## Sheet1
Defect_ID | TestCase_ID | Defect Title | Steps to reproduce | Test Environment | Test Input | Expected result | Actual result | Status | Attachments | Severity | Priority | Date | Tester
D_1 | TC_18 | UI-Readability | 1.open the browser 2. copy and paste url 3.enter 4.verify all words are properly readable | Google Chrome | https://crackerscraze.com/index.php | The Register page is readable | Not As expected(text in signup page is not readable) | new |  | medium | medium | 26-09-2023 | Drisya
D_2 | TC_21 | UI-Readability | 1.open the browser 2. copy and paste url 3.enter 4.verify all words are properly readable | Google Chrome | https://crackerscraze.com/index.php | The Register page is readable | Not As expected(text in signin page is not readable) | new |  | medium | medium | 26-09-2023 | Drisya
D_3 | TC_31 | HomePage_functionality | 1.open the browser 2. copy and paste url 3.enter 4.click on crackers mailid link | Google Chrome | https://crackerscraze.com/index.php | The link should go to corresponding mailing page | Not as Expected(link is not working) | new |  | medium | medium | 26-09-2023 | Drisya
D_4 | TC_40 | Signup_functionality | 1.open the browser 2. copy and paste url 3.enter 4.enter all signup details 5.llogin | Google Chrome | https://crackerscraze.com/index.php | Signup successfully message | Not as expected(no message whether signup successful or not) | new |  | medium | medium | 26-09-2023 | Drisya
D_5 | TC_42 | Signup_functionality | 1.open the browser 2. copy and paste url 3.enter 4.enter invalid ph num and valid pwd 5.llogin | Google Chrome | https://crackerscraze.com/index.php | Unable to login and shows an error msg | Not as expected(invalid email or password msg occurs instead of invalid ph nmbr) | new |  | High | High | 26-09-2023 | Drisya
D_6 | TC_43 | Signup_functionality | 1.open the browser 2. copy and paste url 3.enter 4.enter password | Google Chrome | https://crackerscraze.com/index.php | password hidden icon correctly given | Not as expected(pwd hidden icon wrongly given) | new |  | High | High | 26-09-2023 | Drisya
D_7 | TC_46 | Signup_functionality | 1.open the browser 2. copy and paste url 3.enter 4.enter all signup details 5.llogin | Google Chrome | https://crackerscraze.com/index.php | Unable to login and shows an error msg | Not as expected | new |  | medium | medium | 26-09-2023 | Drisya
D_8 | TC_53 | Cart_functionality | 1.open the browser 2. copy and paste url 3.enter 4.click on add cart Button 5.delete cart 6.click continue shopping7.add products 7.click proceed button 8.verify COD | Google Chrome | https://crackerscraze.com/index.php | do not go to payment | Not As expected | new |  | High | High | 26-09-2023 | Drisya
D_9 | TC_54 | Cart_functionality | 1.open the browser 2. copy and paste url 3.enter 4.click on add cart Button 5.delete cart 6.click continue shopping7.add products 7.click proceed button 8.verify Online payment | Google Chrome | https://crackerscraze.com/index.php | go to payment gateway | Not As expected(not going to payment gateway) | new |  | medium | medium | 26-09-2023 | Drisya
D_10 | TC_58 | Signup_functionality | 1.open the browser 2. copy and paste url 3.enter 4.login 5.profile update | Google Chrome | https://crackerscraze.com/index.php | Profile should update Successfull | Not As expected(not updating | new |  | High | High | 26-09-2023 | Drisya
D_11 | TC_67 | Signup_functionality | 1.open the browser 2. copy and paste url 3.enter 4.enter password in capital letter | Google Chrome | https://crackerscraze.com/index.php | Not Able to login as a new user | Not as expected | new |  | medium | medium | 26-09-2023 | Drisya
Types of test Performed :
Types : | Status
Unit Testing | failed
Integration Testing | passed
System Testing | passed
Acceptance Testing | failed
Compatibility Testing | passed
Functional Testing | failed
Useability Testing | passed
Non Functional Testing | passed
End to End Testing | passed
Regresstion Testing | failed